## Sheet1
PROJECT SCHEDULE
ID | Task |  | Resource(s) | Year | Year 1 | [51 empty] | Year 2 | [51 empty] | Status (Open/ Complete)
|  |  |  | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Initiation Phase
1 |  | Recruit Project Team | PI | bar: Year 1 1 to Year 1 4
2 |  | Project Kick-Off Meeting | All Team | bar: Year 1 4
3 |  | Gain Access to Office & Technical Resources | PI | bar: Year 1 4
4 |  | Analyse Project Brief | All Team | bar: Year 1 5 to Year 1 6
5 |  | Create Document Library | PI | bar: Year 1 6
6 |  | Initiation Phase Complete | bar: Year 1 6
Definition and Planning Phase
7 |  | Gather Requirements | All Team | bar: Year 1 7 to Year 1 8
8 |  | Requirements Analysis | All Team | bar: Year 1 9 to Year 1 11
9 |  | Create Project Schedule | PI | bar: Year 1 11 to Year 1 12
10 |  | Risks Analysis | All Team | bar: Year 1 11 to Year 1 12
11 |  | Create Risk Register | PI | bar: Year 1 12
12 |  | Define Roles & Responsibility (RACI Matrix) | PI | bar: Year 1 12
13 |  | Apply for IRB/Research Ethics Approval | Soft OR Resource | bar: Year 1 13 to Year 1 18
14 |  | Definition and Planning Phase Complete | bar: Year 1 18
Execution Phase
15 |  | Recruit Research Participants | Soft OR Resource | bar: Year 1 19 to Year 1 29
16 |  | Data Collection (e.g. Workshops/Interviews) | Soft OR Resource | bar: Year 1 25; Year 1 27; Year 1 29
17 |  | Qualitative Data Analysis | Soft OR Resource | bar: Year 1 30 to Year 1 37
18 |  | Social Network Analysis | Modeller | bar: Year 1 36 to Year 1 41
19 |  | Soft Systems Methodology Analysis | Modeller | bar: Year 1 42 to Year 1 47
20 |  | Develop Conceptual Model | Soft OR Resource, Modeller | bar: Year 1 48 to Year 1 51
21 |  | Validation of Conceptual Model | All Team | bar: Year 1 51
22 |  | Develop Technical Design | Modeller | bar: Year 1 52 to Year 2 3
23 |  | Develop Agent-Based Model | Modeller | bar: Year 2 4 to Year 2 11
24 |  | Calibration of Agent-Based Model | Modeller | bar: Year 2 12 to Year 2 13
25 |  | Agent-Based Model Sensitivity Analysis | Modeller | bar: Year 2 14 to Year 2 15
26 |  | Validation and Verification of Agent-Based Model | Modeller | bar: Year 2 16 to Year 2 17
27 |  | Simulation-Based Experimentation | Modeller | bar: Year 2 18 to Year 2 33
28 |  | Analyse Simulation Output Data | All Team
29 |  | Develop Qualitative Analysis and SNA Manuscript | All Team | bar: Year 1 42 to Year 2 1
30 |  | Develop Conceptual Modelling Manuscript | All Team | bar: Year 1 52 to Year 2 11
31 |  | Develop ABM Manuscript | All Team | bar: Year 2 34 to Year 2 49
32 |  | Execution Phase Complete | bar: Year 2 49
Monitoring and Control Phase
33 |  | Review and Update Risk Register | PI | bar: Year 1 13 to Year 2 33
34 |  | Review and Update Schedule | PI | bar: Year 1 9 to Year 2 49
35 |  | Review Issues | PI | bar: Year 1 19 to Year 2 49
36 |  | Weekly Progress Reports | Soft OR Resource, Modeller
37 |  | Monitoring and Control Phase Complete | bar: Year 2 49
Closure Phase
38 |  | Upload Primary Data Set to Repository | Soft OR Resource | bar: Year 2 50
39 |  | Upload Agent-Based Model Code to Repository | Modeller | bar: Year 2 50
40 |  | Upload Simulation Output Data to Repository | Modeller | bar: Year 2 50
41 |  | Develop End of Project Report for Funder | PI | bar: Year 2 51 to Year 2 52
42 |  | Closure Phase Complete | bar: Year 2 52
Project Complete | bar: Year 2 52