## Sheet1
RACI Matrix
Project Schedule ID | Task | PI | Soft OR Resource | Modeller | Research Participants | Funder
6 | Document Library | A, R | C, I | C, I
8 | Reqts Analysis | A, R | C, I | C, I
9 | Project Schedule | A, R | C, I | C, I
11 | Risk Register | A, R | R, C, I | R, C, I
12 | RACI Matrix | A, R | C, I | C, I
13 | IRB/Ethics Approval | A | R | C, I
15 | Recruit Participants | C, I | A, R | C, I | C
16 | Data Collection | C, I | A, R | C, I | C
17 | Quals Analysis | C, I | A, R | C, I
18 | SNA | C, I | C, I | A, R
19 | SSM Analysis | C, I | A, R | C, I
20 | Conceptual Model | A | R | R
22 | Technical Design | C, I | C, I | A, R
23 | ABM | A | C, I | R
27 | Simulations | A | C, I | R
29 | Quals Manuscript | A | R | C, I
30 | Conc Model Manuscript | A | R | R
31 | ABM Manuscript | A | C, I | R
41 | End Project Report | A, R | C, I | C, I |  | I
Key:
R = Responsible - People or stakeholders who do the work. They must complete the task or objective. Several people can be jointly Responsible.
A = Accountable - Person or stakeholder who is the "owner" of the work. He or she must sign-off or approve task when complete. Only one person can be Accountable.
C = Consulted - People or stakeholders who need to give input before the work can be done and signed-off. These people are "in the loop" and active participants.
I = Informed - People or stakehodlers who need to be kept "in the picture". They need updates on progress or decisions, but they do not need to be formally consulted, nor do they directly contribute.