## Sheet1
Stakeholder Matrix
Stakeholder | Role in Project | Perception of Project (+ve, -ve, neutral) | What they want from the Project | What they want to know about status/progress | How they will be engaged by the Project Team | Who within the Project Team will engage with them | Frequency/Timing
Principal Investigator | PI and Project Manager | Positive | Successful project, Excellent data, Pipeline of Excellent manuscripts, Increase rresearch reputation | Everything | Informally by other team members | Everyone | Daily
Soft OR Resource | Functional Resource | Positive | Successful project, Excellent qualitative data, first author of quals manuscript and co-author on other manuscripts, Increase rresearch reputation to facilitate employment on future projects or gain an academic career | Everything | Informally by other team members | Everyone | Daily
Modeller | Technical Resource | Positive | Successful project, Excellent qualitative data, first author of ABMS manuscript and co-author on other manuscripts, Increase rresearch reputation to facilitate employment on future projects or gain an academic career | Everything | Informally by other team members | Everyone | Daily
Research Participants | Research Participants | Neutral | Opportunity to discuss experiences of conflict in projects that they've been involved in, help shape requirements of the project to align with their experiences of conflict in projects, to be kept aware of outcomes from this research project | Interview/Workshop schedule and format. Longer-term project outcomes and sight of publications. | Formally by PI through online funders reporting system | Soft OR Resource and PI | Ad hoc at beginning of project
Funder | Provide funds to PI | Positive | Successful project that provides return on investment through publications, real-world impact and engagement | Periodic progress reports; finance reports; end of project report; publications, conferences and dissemination activities; impact on real-world domain | Informally by Soft OR Resource regarding scheudling of interviews/workshops and formally by PI at end of project to being provided copies of some project outputs | PI | At formal reporting milestones set by Funder and then annually to record publications/impact.